## ENSE 271 Final Project Local
Activity | Task | Subtask | Subtask description | Status | Estimation | Release | Personas | SecondLevelPersonas | ThirdLevelPersonas | ActivityColor | TaskColor | SubtaskColor | FirstLevelAnnotations | SecondLevelAnnotations | ThirdLevelAnnotations | ExternalKey | BasicPrioValue | MoscowPrioValue | KanoPrioValue | BusinessValue | Effort
Home | UI Local Data sorted by Cause | Display the Sorted Causes |  | Todo | 3.00 | Minimum Viable Products (MVP) | [10 empty] | 2 |  |  | 5 | 2
Home | Provide the list of SDGs | Small bar type graph to display score |  | Todo | 3.00
Home | Provide the list of SDGs | Description | Small info (2-3 sentences possibly) paired with video link and images. | Todo | 2.00 | Minimum Viable Products (MVP) | [10 empty] | 2 |  |  | 5 | 2
Home | Provide the list of SDGs | Link for why it's important for this community and city |  | Todo | 2.00 | Minimum Viable Products (MVP)
Home | Search bar | Filter industry, SDG, etc. |  | Todo | 5.00 | Minimum Viable Products (MVP)
Home | Search bar | Sort by alphabets and/or numbers |  | Todo | 6.00 | Minimum Viable Products (MVP)
Home | Search bar | Recommendations |  | Todo | 3.00 | Before Going Public
Home | Volunteer and Community Services | List where good volunteers are displayed due to their incredible work. |  | Todo | 5.00
Home | Volunteer and Community Services | Provide a list of charities and/or communities involved |  | Todo | 5.00 | Minimum Viable Products (MVP)
Home | Volunteer and Community Services | How can you help? |  | Todo | 5.00 | Minimum Viable Products (MVP)
Home | Volunteer and Community Services | Background information on non-profits |  | Todo | 3.00 | Before Going Public
Home | About Information | Who we are section |  | Todo | 3.00 | Minimum Viable Products (MVP)
Home | About Information | Why it matters section |  | Todo | 4.00 | Minimum Viable Products (MVP)
Home | About Information | Land Acknowledgement |  | Todo | 3.00 | Minimum Viable Products (MVP)
Home | About Information | Details about impact of volunteering on our society. |  | Todo | 5.00 | Before Going Public
Browse Data & SDG mapping | Display SDG Information and Mapping | Contact information |  | Todo | 3.00
Browse Data & SDG mapping | Display SDG Information and Mapping | Provide SDG context and information on each |  | Todo | 5.00 | Minimum Viable Products (MVP) | [10 empty] | 2 |  |  | 5
Browse Data & SDG mapping | Display SDG Information and Mapping | Provide Graphs of SDG Trends |  | Todo | 8.00 | Minimum Viable Products (MVP) | [10 empty] | 2 |  |  | 5
Browse Data & SDG mapping | Display SDG Information and Mapping | Interactive feature for engagement | Due to the fact that people can get bored or lose interest easily...This may distinguish immersiveness. For instance, if we were to explore SDG Water Use, there can be a looped animated gif of faucet water running. Then if tapped (or some sort of interaction), it will show another animation of no more water leakage. | Todo | 8.00 | Minimum Viable Products (MVP) | [8 empty] | Needs discussion
Browse Data & SDG mapping | Display SDG Information and Mapping | What can you do to help us achieve our goals for the City of Regina? |  | Todo | 5.00 | Minimum Viable Products (MVP) | [10 empty] | 2 |  |  | 5
Browse Data & SDG mapping | Display Local (Regina) Data and Information | Display data in some form | # Data shown (with a filter)... - Chart - Graph - Percentage scale | Todo | 8.00 | Minimum Viable Products (MVP) | [10 empty] | 2 |  |  | 5
Browse Data & SDG mapping | Display Local (Regina) Data and Information | Share/Download button | Share to social media apps (Facebook, Instagram, Twitter, etc). Download to device. | Todo | 10.00 | Minimum Viable Products (MVP) | [10 empty] | 2 |  |  | 5
Note on B3: Will include info on what the SDG is. Link to local data relating to each SDG and non-profits that help achieve that SDG

## Releases
Name | Goal | Start date | Release date | Is released | Is archived
Minimum Viable Products (MVP) |  |  |  | False | False
Before Going Public |  |  |  | False | False

## Workflowsettings
State color | State name | State category | Key
#A1ABB9 | Todo | 10 | 1
#396AFF | Doing | 20 | 2
#FF3C39 | Ready | 20 | 3
#3DC11E | Done | 30 | 4

## Annotations
Name | Icon | Color | Emoji | IsArchived
Rejected | 400 | 7 |  | False
Splittable | 740 | 3 |  | False
Risk | 170 | 6 |  | False
Needs discussion | 290 | 3 |  | False
Idea | 390 | 5 |  | False
Blocked | 120 | 7 |  | False
Depends on other | 540 | 7 |  | False